## v1
The King of Spades Project v1
| Current Version |  | Game Completed: |  | Last Updated:
| v1.8.1 |  | 96.5 | % | `7/3/2006
Version Description
You can now use superpowers to travel, perform surveillance.
Update Notes:
Setting up infiltration, room/building damage, Magik
Next update upload (Estimated):
2006-08-15
Version Update
Version | Projected | Module | Description |  |  |  | Status | Update Notes
2002-09-01
v1.0 |  | Shopping | You can now buy stuff |  |  |  | 100% | Completed.
v1.1 |  | Chat | You can now chat and direct your messages to someone specific |  |  |  | 100% | Completed.
2002-10-01
v1.2 |  | Shopping | You can go to shops and train/practice your skills. |  |  |  | 100% | Completed.
v1.2.1 |  | Interface | The Inventory, description screens now load in the control screen, less pop-ups and easier game-playing! |  |  |  | 100% | Completed.
v1.3 |  | Inventory | You can see your items. |  |  |  | 100% | Completed.
v1.3.1 |  | Chat | You can now see other people and trade with them. |  |  |  | 100% | Completed.
v1.4 |  | Buildings | You can now enter buidings and chat in lounges. |  |  |  | 100% | Completed.
v1.5 |  | Teams | You can now choose your team or create a new one |  |  |  | 100% | Completed.
2003-07-01
v1.6.0 |  | Combat | You can now train your hand-2-hand combat skills and wield a weapon. |  |  |  | 100% | Completed.
v1.6.1 |  | Combat | You can now fight using hand-2-hand combat techniques. |  |  |  | 100% | Completed.
v1.6.2 |  | Combat | You can now fight using superpowers. |  |  |  | 100% | Completed.
v1.6.3 |  | Combat | You can now fight using ALL weapons |  |  |  | 100% | Completed.
v1.7 |  | Vehicles | You can now buy a vehicle and use it to carry heavy things (Cargo) |  |  |  | 100% | Completed.
v1.7.1 |  | Vehicles | You can now ride your vehicles and park them. |  |  |  | 100% | Completed.
|  | Vehicles | You can now have passengers in your car. |  |  |  | 100% | Completed.
|  | Locations | Staten Island, Queens, The Bronx and Manhattan now open, if you don't have a vehicle you can take a bus or subway to go to the other sections of the city. |  |  |  | 100% | Completed.
Miscellaneous Updates
|  | NPCs | You can now buy pets and hire vendors and assign them to do specific jobs. |  |  |  | 100% | Completed.
|  | Travel | You can now travel to any coordinates. |  |  |  | 100% | Completed.
|  | Profile | You can now edit your profile. |  |  |  | 99% | Can Delete characters. Nead to work on filters.
|  | Interface | Entire control screen will be revamped to have drop-down menus instead of clickable links. |  |  |  | 100% | Completed.
|  | Relationships | You can now send memos to players who are offline. These players must have some kind of relationship to you (E.g. friends, team-members, etc.) |  |  |  | 100% | Completed.
|  | Locations | The hospital can now be accessed and you can go to heal yourself, increase your mental stability (the mental ward), etc. |  |  |  | 100% | Completed.
|  | Shopping | You can now go into the time agency and buy and sell time units |  |  |  | 100% | Completed.
|  | Attributes | Skill capacity to be set. You can have a maximum of 3 combat styles, 20 skills and 5 superpowers. Only premium members will be able to increase their limit. Players who have already exceeded their limits will have the opportunity to sell the skills they don't want in return for cash equalling about 75% of the original skill cost/point. |  |  |  | 100% | Completed.
|  | Locations | You can now store items in your room. |  |  |  | 100% | Completed.
v1.8 | 2004-11-21 | Land & Construction | You can now manage your land and construct land and subterranean structures. |  |  |  | 100% | Completed.
v1.8.1 | 2004-11-30 | Quests | You can now go on NPC adventure quests created by GMs |  |  |  | 100% | Completed.
v1.8.2 | 2004-12-30 | Missions | Players can now travel to underwater, aerial and underground locations. |  |  |  | 100% | Completed.
v1.9 | 2006-09-15 | Levels | You can now upgrade your levels by going on Missions and Quests, gaining relationships and fighting. |  |  |  | 96% | Completing missions module and automated missions downloading.
v1.9.1 | 2006-10-01 | Space | Players can now travel in space using space ships. |  |  |  | 50% | Ship set-up. Manual consoles set-up. Setting up automatic consoles.
Alpha | 2006-11-12 | All | Set up all superpower, job and skill functionality. |  |  |  | 83% | Working on Magik, Leech superpower
Total Modules: |  | 30 |  |  | Project Completed: |  | 96.5 | %

## v2
The King of Spades Project v2
| Current Version |  | Game Completed: |  | Last Updated:
| Not started |  | 0 | % | `7/3/2006
Version Description
Update Notes:
Next update upload (Estimated):
2007-07-01
Version Update
Version | Projected | Module | Description |  |  |  | Status | Update Notes
2007-02-01
v2.0 |  | Front page | Upgrade of front page |  |  |  | 0%
v2.1 |  | GUI | Upgrade the GUI to support Flash or ActiveX |  |  |  | 0%
2007-04-01
v2.2 |  | Day & Night | Day and night is now dynamic. Different effects for different races |  |  |  | 0%
v2.2.1 |  | Weather | Weather is manipulated by superpowers or GMs. |  |  |  | 0%
v2.3 |  | Satellites | Satellites can be launched in space. Used for spying or communications |  |  |  | 0%
v2.3.1 |  | Comms | You can now set up TV, radio stations, etc. |  |  |  | 0%
v2.4 |  | Radars | You can set up Radars and defence arrays for attacking enemy vehicles |  |  |  | 0%
v2.5 |  | Research | You can set up a server and networks to aid in research |  |  |  | 0%
v2.5.1 |  | Hacking | People can hack into others' networks and steal data. |  |  |  | 0%
2007-08-01
v2.6 |  | Vehicles | You can now set up weapons and artillery on vehicles |  |  |  | 0%
v2.6.1 |  | Vehicles | You can now manouver your vehicles for combat |  |  |  | 0%
2007-09-01
v2.7 |  | Doomsday | Malignants and Anarchists can create doomsday devices to threaten the Earth and other realms |  |  |  | 0%
v2.8 |  | Manufacturing | Factories can now mass produce a prototype |  |  |  | 0%
Miscellaneous Updates
Alpha | 2008-01-01 | All | Set up all research and manufacturing capabilities |  |  |  | 0%
Total Modules: |  | 30 |  |  | Project Completed: |  | 0 | %